## Sheet1
PCL
Project: |  | ECC Theatre Renovation
Look Ahead Schedule
ID |  | Activity | [36 empty] | MAY | [27 empty] | JUNE
|  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
|  |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T |  |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | NOTES
| Construction Activities |  | Responsible | [33 empty] | PCL Resp. | Shift* | bar: MAY 5 M to MAY 9 F; MAY 12 M to MAY 16 F; MAY 19 M to MAY 23 F; MAY 26 M to MAY 30 F; JUNE 2 M to JUNE 6 F; JUNE 9 M to JUNE 13 F; JUNE 16 M to JUNE 20 F; JUNE 23 M to JUNE 27 F; JUNE 30 M to JUNE 4 F
Preconstruction
Contractor Onboarding
|  | Letters of Intent Sent to Contractors | SDCCD | bar: MAY 9 F
Board Approval Date | bar: MAY 15 T
|  | Draft Contract Agreements Sent to Contractors | SDCCD | bar: MAY 19 M to MAY 20 T
|  | CBA Documents Due From Contractors | Primes | bar: MAY 27 T
|  | CBA Documents Due to Unions | Casamar | bar: MAY 28 W
|  | CBA Pre-Job Conference | Casamar | bar: JUNE 4 W
Mobilization
Moving Activities
|  | Staff Office Move | [35 empty] | Day | bar: JUNE 2 M to JUNE 6 F
|  | Cultural Artifact Move # 1 | [35 empty] | Day | bar: JUNE 5 T to JUNE 6 F; JUNE 9 M to JUNE 10 T
|  | Move Pantry | [35 empty] | Day | bar: JUNE 13 F
|  | Cultural Artifact Move #2 | [35 empty] | Day | bar: JUNE 9 M to JUNE 13 F
Mobilization
|  | Install Cones / No Parking Signs for Pantry | [35 empty] | Day | bar: JUNE 4 W
|  | MEP Investigation for Trailers | [35 empty] | Day | bar: JUNE 5 T to JUNE 6 F
|  | Install Temp Pantry Trailer | [35 empty] | Day | bar: JUNE 5 T to JUNE 6 F
|  | Connect Temp Power/Water to Pantry | [35 empty] | Day | bar: JUNE 9 M to JUNE 11 W
|  | Install Detour/Wayfinding Fignage | [35 empty] | Day | bar: JUNE 10 T
|  | Temp Signage Site Walk | [35 empty] | Day | bar: JUNE 11 W
|  | Install Cones / No Parking Signs for Striping | [35 empty] | Day | bar: JUNE 12 T
|  | Temp Striping For Parking | [35 empty] | Day | bar: JUNE 13 F
|  | Install Temp ADA Ramp | [35 empty] | Day | bar: JUNE 12 T
|  | Set Perimeter Fence At Trailer (Phase 1) | [35 empty] | Day | bar: JUNE 16 M to JUNE 20 F
|  | Install Temporary Toilets | [35 empty] | Day | bar: JUNE 17 T to JUNE 18 W
|  | Set Construction Trailers | [35 empty] | Day | bar: JUNE 19 T to JUNE 20 F; JUNE 23 M to JUNE 25 W
|  | Connect Temp Power/Water to Trailers | [35 empty] | Day | bar: JUNE 23 M to JUNE 27 F
|  | Set Perimeter Fence at Construction Zone (Phase 2) | [35 empty] | Day | bar: JUNE 23 M to JUNE 27 F
|  | Fire Department Walk | [35 empty] | Day | bar: JUNE 27 F
|  | Install Construction Banners Around Permiter Fence | [35 empty] | Day | bar: JUNE 23 M to JUNE 24 T
|  | Install Interior Temporary Partition | [35 empty] | Day | bar: JUNE 26 T to JUNE 27 F
Construction Safe-off
|  | MEP Investigation for Safe-off | [35 empty] | Day | bar: JUNE 12 T to JUNE 13 F; JUNE 16 M to JUNE 20 F; JUNE 23 M to JUNE 27 F
|  | Submit Utility Shutdown Request Form | [35 empty] | Day | bar: JUNE 16 M
|  | Theatre Safe-off | [35 empty] | Day | bar: JUNE 30 M to JUNE 4 F